## Sheet1
| Task | Estimate | Actual
1 | Setup Project | 4 | 9.43
2 | Setup Scene manager | 2 | 1.2
3 | Player Controls | 30 | 56
4 | Tree Collisions | 10 | 7.54
5 | Soldier Logic | 20 | 25.23
6 | Hospital Logic | 15 | 16.32
7 | Game Over/Win Screen | 20 | 10.24
8 | Assets/sprites | 30 | 26.5